## Timeline
Group 1 - Project Timeline
PROJECT TITLE |  | Real Estate Data Team Website Analysis & Data Visualization Report |  |  |  |  | COMPANY NAME | [8 empty] | House730
PROJECT MANAGER |  | Kris |  |  |  |  | TEAM NAME | [8 empty] | Data Analytics Team
[7 empty] | DATE | [8 empty] | 2023-06-24
TASK NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [6 empty] | PHASE TWO | [6 empty] | PHASE THREE | [6 empty] | PHASE FOUR | [6 empty] | PAHSE FIVE | [6 empty] | PROJECT END
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
[7 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Project Proposal
1.1 | Dataset Decision | Hin, Kris, Jensen | 2023-06-19 | 2023-06-24 | 5 | 100% | WEEK 5 S: PROJECT END
1.2 | Project Objectives | Hin, Kris, Jensen | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 T
1.3 | Data Study for Methodology | Hin, Kris | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 T
1.4 | Tableau Study | Hin, Kris | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 T
1.5 | Project Timeline | Kris | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 T
1.6 | Data Web Scraping - Initial Stage | Jensen | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 F
1.7 | Project Proposal Completion | Hin, Kris, Jensen | 2023-06-24 | 2023-06-30 | 6 | 100% | bar: WEEK 1 S to WEEK 2 F
2 | Project Design
2.1 | Scope and Goal Setting - Dashboard | Hin, Kris, Jensen | 2023-06-27 | 2023-06-30 | 3 | 100% | bar: WEEK 2 T to WEEK 2 F
2.2 | Data Architecture design | Hin, Kris | 2023-06-27 | 2023-06-30 | 3 | 100% | bar: WEEK 2 T to WEEK 2 F
2.3 | Data Web Scraping - Data Type Design | Jensen | 2023-06-30 | 2023-07-02 | 2 | 100% | bar: WEEK 2 F to WEEK 2 S
3 | Development
3.1 | Dashboard Design | Hin, Kris, Jensen | 2023-07-03 | 2023-07-11 | 8 | 100% | bar: WEEK 3 M to WEEK 4 T
3.1.1 | Dashboard 1 | HIn | 2023-07-03 | 2023-07-11 | 8 | 100% | bar: WEEK 3 M to WEEK 4 T
3.1.2 | Dashboard 2 | Kris | 2023-07-03 | 2023-07-11 | 8 | 100% | bar: WEEK 3 M to WEEK 4 T
3.1.3 | Dashboard 3 | Jensen | 2023-07-03 | 2023-07-11 | 8 | 100% | bar: WEEK 3 M to WEEK 4 T
3.2 | Progress Update | Hin, Kris, Jensen | 2023-07-07 | 2023-07-11 | 4 | 100% | bar: WEEK 3 F to WEEK 4 T
3.3 | Development Debug/Re-design (If any) | Hin, Kris, Jensen | 2023-07-09 | 2023-07-11 | 2 | 100% | bar: WEEK 3 S to WEEK 4 T
4 | Testing
4.1 | Test Dashboard | Hin, Kris, Jensen | 2023-07-11 | 2023-07-14 | 3 | 100% | bar: WEEK 4 T to WEEK 4 F
4.2 | Test Tableau Publish | Hin, Kris, Jensen | 2023-07-11 | 2023-07-14 | 3 | 100% | bar: WEEK 4 T to WEEK 4 F
5 | Release
5.1 | Publish Dashboard Public | Hin, Kris, Jensen | 2023-07-14 | 2023-07-15 | 1 | 100% | bar: WEEK 4 F to WEEK 4 S
6 | Project Report
6.1 | Report | Hin, Kris, Jensen | 2023-07-15 | 2023-07-22 | 7 | 100% | bar: WEEK 4 S to WEEK 5 S